## Sheet1
Requirement ID | Description of Requirement | Story Points | Priority | Sprint No.
1 | Data Injestion from Simulator / PLC device | 8 | 1
2 | Basic data sanitzation & normalization | 3 | 1
3 | Basic ML Anomaly Detection | 8 | 1
4 | Live Dashboard w / Basic Display | 5 | 1
5 | Data Storage for logs / time windows | 3 | 2
6 | Configurable manual anomaly thresholds | 2 | 2
7 | System Status / Health Indicators | 2 | 2
8 | Fault injection for testing | 5 | 3
9 | Warm-up period for ML (Can be small but configurable) | 2 | 3
10 | Documentation | 2 | 3
11 | Sprint 2 Presentation Setup | 2 | 3
12 | Set up Simulator / PLC device | 5 | 1
13 | ML Clustering model | 8 | 3
14 | Unit Testing certain Segments | 5 | 4
15 | Basic Static Rule alert system | 3 | 4
16 | Exporting Data | 3 | 4
17 | Click PLC Data over modbus | 3 | 4
18 | Advanced ML detection & Control | 8 | 5
19 | Message Broker for message passing | 2 | 5
20 | UI Redesign | 5 | 5
21 | Service selection through site | 2 | 5
22 | Seperate concurrent service ingestion | 2 | 5
23 | Policy Simulation & Access Contracts | 3 | 6
24 | Notification Integrations (Email, slack, etc) | 3 | 6
25 | Adaptive backpressure handling of ingestion | 8 | 6
26 | Event rate and processing metrics | 2 | 6
27 | Retention Policies | 2 | 6
28 | Automated Performance Metrics | 3 | 7
29 | CI / CD Pipeline to ensure passing metrics | 5 | 7
30 | Clustered Anomalies | 8 | 7
31 | ML Classification of anomalies for certian devices i.e: Nuclear | 5 | 7
32 | Authentication & Role-based access to website | 5 | 8
33 | Event timeline access | 3 | 8
34 | ML Cross-compare anomalies to find common patterns | 5 | 8
35 | Advanced Exportable data & reports (PDF ,txt, format, etc) | 5 | 8
36 | Ingestion of HTTP & Modbus device events concurrently | 3 | 8
37 | Readme Update | 1 | 8